## Sheet1
			Intern List of Targets

Sr No.	Task	Start Date	End date	Pending work	Remarks
1	GOOSE code- GG lab & Das Lab	03-06-2024	14-06-2024	Completed
2	GOOSE rest featutes	18-06-2024	26-06-2024	Completed
3	SV GG Lab GitHub	27-06-2024	16-07-2024	Faster packet injection & testing
4	GOOSE offline databse	01-08-2024	05-08-2024	Completed
4	mms offline	26-07-2024		Half way
5	modbus offline	06-08-2024	12-08-2024	Pcap cases , Documentation, Test results
6	wireshark substitute	29-07-2024		More tools, Testing, Documentation
7	dnp3 offline		27-08-2024
8	SV ARP/Dos & Replay	28-08-2024	31-08-2024
9	Modbus replay dos
10

## Sheet2
SV ARP MITM Replay
TCP layer
IEC 104